## Instructions
MarketX — Manual QA Checklist
Two-person split. UI flow + feedback testing (no API).
How to use
1. Each intern works their own tab: 'Intern A' or 'Intern B'.
2. Do the steps in 'Test case', compare to 'Expected result'.
3. Set Status (dropdown). For Fail/Issue, set Severity, Device, Theme and add Notes + a screenshot link.
4. Test each area once on DESKTOP and once on a PHONE; note which breaks. Re-check key screens in DARK mode.
5. Log every Fail/Issue in the 'Defect Log' tab too.
Status values: Pass ¦ Fail ¦ Issue ¦ Blocked ¦ Not tested
Severity: S1 Blocker ¦ S2 Major ¦ S3 Minor ¦ S4 Cosmetic
Test accounts (preview env) — password: test1234
balogun@peppr.test -> seller (chairman), store balogun-fabrics
ada@peppr.test -> seller + buyer, store ada-styles
chidi@peppr.test -> buyer only (no store)
wuse@peppr.test -> other seller, store wuse-fashion
(register a fresh account with a real inbox for sign-up/verify tests)
Split: Intern A = Buyer & Social journey ¦ Intern B = Seller, Money & Community

## Intern A
ID | Area | Test case (steps) | Expected result | Status | Severity | Device | Theme | Notes / screenshot link
0. Cross-cutting UX (check on every screen)
A01 | 0. Cross-cutting UX (check on every screen) | Page loads without a flash of 'not found' / blank-then-content | Smooth load; skeletons while loading
A02 | 0. Cross-cutting UX (check on every screen) | Loading states show a skeleton/shimmer or spinner | Clear loading feedback, not a frozen blank
A03 | 0. Cross-cutting UX (check on every screen) | Empty states (no data) show a message + a next-step button | Helpful empty state, not blankness
A04 | 0. Cross-cutting UX (check on every screen) | Errors show a readable message with retry/recovery | Friendly error + recovery, no raw error/silent fail
A05 | 0. Cross-cutting UX (check on every screen) | Buttons disable + show spinner during an action | No double-submits
A06 | 0. Cross-cutting UX (check on every screen) | Dark mode: text readable, no white-on-white / black-on-black | Legible in both themes
A07 | 0. Cross-cutting UX (check on every screen) | Back button / browser nav returns to the right place | No broken navigation
A08 | 0. Cross-cutting UX (check on every screen) | Images load; avatars fall back to initials | No broken media
1. Register
A09 | 1. Register | Submit Sign-up with empty fields | Inline validation; can't submit
A10 | 1. Register | Enter invalid email (e.g. 'abc') | 'Invalid email' message
A11 | 1. Register | Enter a weak password | Password rule message
A12 | 1. Register | Register with a valid new email + password | Success; verify-email prompt / redirect
A13 | 1. Register | Register again with the same email | 'Email already in use', no crash
1. Email verification
A14 | 1. Email verification | Check inbox for verification email | Email arrives with a link
A15 | 1. Email verification | Click the verify link | 'Email verified' confirmation
A16 | 1. Email verification | Click the same link again | Graceful 'already used/verified', not an error page
A17 | 1. Email verification | Use 'Resend verification' | New email sent; success feedback
1. Login / Logout
A18 | 1. Login / Logout | Login with wrong password | Clear 'incorrect credentials'; no crash
A19 | 1. Login / Logout | Login with correct credentials | Lands on home feed; logged-in (avatar/menu)
A20 | 1. Login / Logout | Refresh the page while logged in | Stays logged in
A21 | 1. Login / Logout | Logout | Logged-out home; protected pages redirect to login
1. Forgot / Reset password
A22 | 1. Forgot / Reset password | Forgot password with a REGISTERED email | 'If the email exists, a link was sent'
A23 | 1. Forgot / Reset password | Forgot password with an UNREGISTERED email | Identical message (no leak)
A24 | 1. Forgot / Reset password | Open reset link, set a new password | Success; can log in with new password
A25 | 1. Forgot / Reset password | Reuse the same reset link again | 'Link expired/used', not a crash
1. Social login (OAuth)
A26 | 1. Social login (OAuth) | Tap Continue with Google / Facebook / TikTok | Provider opens; on approval, logged in
A27 | 1. Social login (OAuth) | Cancel the provider screen | Returns to login, no error page
2. Feeds
A28 | 2. Feeds | Open Home feed | Posts load with media, author, like/comment counts
A29 | 2. Feeds | Switch to Following feed | Posts from people you follow, or empty state to follow
A30 | 2. Feeds | Open Discover | Broader public content loads
A31 | 2. Feeds | Scroll to the bottom | More posts load (infinite scroll), no duplicates
2. Reels
A32 | 2. Reels | Open Reels | First video autoplays
A33 | 2. Reels | Swipe/scroll to next reel | Advances to next video and it plays
A34 | 2. Reels | Mute, then go to next reel | Mute state persists across reels
A35 | 2. Reels | Like / open comments on a reel | Like toggles; comments open
2. Stories
A36 | 2. Stories | Tap a story | Opens full-screen, auto-progresses
A37 | 2. Stories | (Owner) create a story | Uploads and appears in the tray
A38 | 2. Stories | Re-open an expired/24h+ story | Expired stories no longer show
2. Posts
A39 | 2. Posts | Create a text post | Appears in your feed/profile
A40 | 2. Posts | Create an image post and a video post | Media uploads with progress; renders after
A41 | 2. Posts | Like a post, then unlike | Count up then down; no double-count
A42 | 2. Posts | Comment on a post; reply to a comment | Comment + reply appear immediately
A43 | 2. Posts | Tap a @mention in a caption | Navigates to that profile (no post-not-found flash first)
A44 | 2. Posts | Tap a #hashtag | Navigates to that tag's results
A45 | 2. Posts | Open a single post via its link | Post detail loads (no 'post not found' flash)
A46 | 2. Posts | Edit your own post; check someone else's | Can edit yours; no edit option on others'
A47 | 2. Posts | Delete your own post | Removed after confirm
2. Visibility
A48 | 2. Visibility | Create a Private post; view as another user | Private post NOT visible in their feeds/your public profile
A49 | 2. Visibility | Create a Followers-only post | Non-follower can't see; follower can
3. Marketplace & Discovery
A50 | 3. Marketplace & Discovery | Open Market / catalog | Product cards with image, bold price, seller
A51 | 3. Marketplace & Discovery | Open a product detail | Images, price, description, variants, seller link, Add-to-cart
A52 | 3. Marketplace & Discovery | Select a variant | Price/stock updates; out-of-stock disabled
A53 | 3. Marketplace & Discovery | Browse a Category | Only that category's products
A54 | 3. Marketplace & Discovery | Open Deals / Fresh Drops / Pre-loved (Thrift) | Each rail shows relevant products
A55 | 3. Marketplace & Discovery | Search a known product (e.g. 'adire') | Product results
A56 | 3. Marketplace & Discovery | Search a seller name | Store results
A57 | 3. Marketplace & Discovery | Search a username | User results; NO email shown
A58 | 3. Marketplace & Discovery | Search 1 character | No results / 'keep typing' (no error)
A59 | 3. Marketplace & Discovery | Tap a seller from a product | Opens that store's profile
4. Cart
A60 | 4. Cart | Add a product to cart | Cart count increments; toast/confirmation
A61 | 4. Cart | Open cart | Line items, quantities, subtotal
A62 | 4. Cart | Increase/decrease quantity | Totals recalc; can't exceed stock
A63 | 4. Cart | Remove an item | Item gone, totals update; empty-cart state if last
4. Checkout
A64 | 4. Checkout | Proceed to checkout | Address, shipping option, payment, order summary
A65 | 4. Checkout | Checkout with NO delivery address | Prompted to add one
A66 | 4. Checkout | Add/select a delivery address | Saved and selectable
A67 | 4. Checkout | Review shipping options (if shown) | Carrier option(s) + price + ETA; total updates with selection
A68 | 4. Checkout | Confirm summary totals = items + shipping | Math is correct
4. Payment
A69 | 4. Payment | Pay with Paystack (test card) | Paystack screen; success -> order confirmation
A70 | 4. Payment | Cancel/fail the Paystack payment | Returns to checkout; 'not completed'; NO order / NO double charge
A71 | 4. Payment | Place a Pay-on-Delivery order (if available) | Order created as POD; clear messaging
A72 | 4. Payment | After success, check My Orders | New order listed with correct status
5. Orders & Tracking
A73 | 5. Orders & Tracking | Open My Orders | List with status badge, amount, date
A74 | 5. Orders & Tracking | Open an order detail | Items, totals, status, tracking section
A75 | 5. Orders & Tracking | On a delivered order, tap Confirm receipt | Status updates; funds-release messaging
A76 | 5. Orders & Tracking | Try Refuse delivery (eligible order) | Confirmation + status change; refund messaging
A77 | 5. Orders & Tracking | Cancel an unpaid/cancellable order | Cancelled; stock returns where applicable
A78 | 5. Orders & Tracking | Leave a review on an eligible product | Review submits and shows on the product
A79 | 5. Orders & Tracking | Try to review a product you didn't buy | Blocked / not offered
14. Dasah AI (in-app)
A80 | 14. Dasah AI (in-app) | Open the Dasah chat | Opens with a welcome message ('Dasah')
A81 | 14. Dasah AI (in-app) | Ask for a product ('find me a red dress') | Replies with product suggestions/cards
A82 | 14. Dasah AI (in-app) | Tap a suggested product | Opens that product
A83 | 14. Dasah AI (in-app) | Ask it to add something to cart (if supported) | Prompts/confirms before adding
A84 | 14. Dasah AI (in-app) | Send gibberish / empty | Graceful reply, no crash
A85 | 14. Dasah AI (in-app) | Navigate away and back | Chat persists or resets cleanly
15. Map / Location
A86 | 15. Map / Location | Open the Map | Seller pins render
A87 | 15. Map / Location | Tap a pin | Seller preview (name, link to store)
A88 | 15. Map / Location | Filter by category / distance | Pins update
A89 | 15. Map / Location | Check a ghost-mode seller | Hidden / not pin-pointed precisely
16. Final sweep (your areas)
A90 | 16. Final sweep (your areas) | Re-run Feed + Checkout flows on a PHONE | Layouts adapt; nothing cut off; buttons reachable
A91 | 16. Final sweep (your areas) | Re-check 5 key screens in DARK mode | Readable, on-brand
A92 | 16. Final sweep (your areas) | Check copy for typos / brand naming ('Dasah','MarketX') | Consistent naming

## Intern B
ID | Area | Test case (steps) | Expected result | Status | Severity | Device | Theme | Notes / screenshot link
0. Cross-cutting UX (check on every screen)
B01 | 0. Cross-cutting UX (check on every screen) | Page loads without a flash of 'not found' / blank-then-content | Smooth load; skeletons while loading
B02 | 0. Cross-cutting UX (check on every screen) | Loading states show a skeleton/shimmer or spinner | Clear loading feedback, not a frozen blank
B03 | 0. Cross-cutting UX (check on every screen) | Empty states (no data) show a message + a next-step button | Helpful empty state, not blankness
B04 | 0. Cross-cutting UX (check on every screen) | Errors show a readable message with retry/recovery | Friendly error + recovery, no raw error/silent fail
B05 | 0. Cross-cutting UX (check on every screen) | Buttons disable + show spinner during an action | No double-submits
B06 | 0. Cross-cutting UX (check on every screen) | Dark mode: text readable, no white-on-white / black-on-black | Legible in both themes
B07 | 0. Cross-cutting UX (check on every screen) | Back button / browser nav returns to the right place | No broken navigation
B08 | 0. Cross-cutting UX (check on every screen) | Images load; avatars fall back to initials | No broken media
Login (prerequisite)
B09 | Login (prerequisite) | Log in as seller balogun@peppr.test | Seller dashboard accessible
B10 | Login (prerequisite) | Log in as ada / chidi / wuse as needed | Each logs in correctly
9. Become a seller
B11 | 9. Become a seller | Open 'Create store' (use buyer-only account) | Store creation form shows
B12 | 9. Become a seller | Submit with a taken store name/slug | Rejected with a message
B13 | 9. Become a seller | Create a valid store | Store created; redirected to dashboard
9. Dashboard & analytics
B14 | 9. Dashboard & analytics | Open seller dashboard | Key stats / quick actions
B15 | 9. Dashboard & analytics | Open Analytics; change the date range | Sales/revenue/orders show; range updates charts
9. Products
B16 | 9. Products | Open Products | Your products (published + drafts) with status
B17 | 9. Products | Create a product (title, price, desc, image, variant+stock) | Saves; appears in list
B18 | 9. Products | Create with price 0 / missing title | Validation blocks it
B19 | 9. Products | Edit a product (price/stock) | Saves; reflected on storefront
B20 | 9. Products | Delete/archive a product | Removed/hidden after confirm
B21 | 9. Products | Confirm a DRAFT product is not visible to buyers | Only published show publicly
9. Orders & messages
B22 | 9. Orders & messages | Open seller Orders | Incoming orders with status
B23 | 9. Orders & messages | Update an order status (mark Shipped) | Status changes; buyer sees it
B24 | 9. Orders & messages | Open store Messages | Customer conversations list
B25 | 9. Orders & messages | Open a customer conversation and REPLY | Message sends (seller can read AND reply to own store chats)
9. Store settings & public page
B26 | 9. Store settings & public page | Edit store settings (logo, banner, desc, ship-from) | Saves; public page updates
B27 | 9. Store settings & public page | View your public store page as a buyer | Products/wall/follow; NO private data (no GPS/phone/verification leak)
B28 | 9. Store settings & public page | Deactivate then reactivate the store | Store hidden/shown accordingly
6. Wallet & Payouts
B29 | 6. Wallet & Payouts | Open buyer wallet | Balance + transactions (or empty state)
B30 | 6. Wallet & Payouts | Open seller wallet | Balance, transactions, payout option
B31 | 6. Wallet & Payouts | Open Payout/Withdraw | Available balance + fee/preview
B32 | 6. Wallet & Payouts | Try to withdraw MORE than balance | Blocked with a clear message
B33 | 6. Wallet & Payouts | Add a bank account; set it default | Saved; default badge moves correctly
B34 | 6. Wallet & Payouts | Try to withdraw with NO bank account | Prompted to add one first
7. Affiliate / Referral
B35 | 7. Affiliate / Referral | Open the Affiliate section (not enrolled) | 'Enrol' call-to-action
B36 | 7. Affiliate / Referral | Enrol as an affiliate | A unique affiliate code is shown
B37 | 7. Affiliate / Referral | Re-open / re-enrol | The SAME code (no duplicate)
B38 | 7. Affiliate / Referral | Browse promotable products | List of products you can promote
B39 | 7. Affiliate / Referral | Copy/share a referral link | Link copies; contains your code
B40 | 7. Affiliate / Referral | Open the affiliate dashboard | Total earnings, pending vs released, conversions
B41 | 7. Affiliate / Referral | (Seller) view Promoters | List of promoters (or empty state)
8. Profile & Social Graph
B42 | 8. Profile & Social Graph | Open your own profile | Avatar, bio, posts, counts, Edit button
B43 | 8. Profile & Social Graph | Edit profile (name, bio, avatar, website) | Saves; changes reflected
B44 | 8. Profile & Social Graph | Add a website link with 'javascript:' / weird scheme | Rejected / sanitised (not clickable as script)
B45 | 8. Profile & Social Graph | Open another user's profile | Follow button (no Edit); their public posts only
B46 | 8. Profile & Social Graph | Follow them; then unfollow | Counts update; button toggles
B47 | 8. Profile & Social Graph | Try to follow yourself | Not possible
B48 | 8. Profile & Social Graph | Open Followers / Following lists | Lists load
B49 | 8. Profile & Social Graph | Open Settings | Loads and saves
B50 | 8. Profile & Social Graph | Check Saved / Liked items | Show what you saved/liked (or empty state)
10. Squares (Community)
B51 | 10. Squares (Community) | Open Squares | List of squares to browse
B52 | 10. Squares (Community) | Open a square | Feed, members, Join/Follow, tabs (All / Requests)
B53 | 10. Squares (Community) | Join / follow a square | Membership/follow state updates
B54 | 10. Squares (Community) | (Buyer, following) post a buyer request | Appears in Requests tab + 'Buyers looking for' strip
B55 | 10. Squares (Community) | Type a phone number in the request note | Masked ([hidden]) when saved
B56 | 10. Squares (Community) | (Member seller) respond to a request with a product | Offer attaches; buyer is notified
B57 | 10. Squares (Community) | (Buyer) accept an offer | Routes to checkout/cart; request marked fulfilled
B58 | 10. Squares (Community) | Post a request WITHOUT following the square | Blocked / prompted to follow
B59 | 10. Squares (Community) | Open square Admin (as chairman) | Member approve/reject, announcements
11. Wall (timeline)
B60 | 11. Wall (timeline) | Open a store's wall as a guest (logged out) | Public posts + shoutouts; no private posts
B61 | 11. Wall (timeline) | (Logged in) leave a shoutout on a store wall | Appears on the wall; owner notified
B62 | 11. Wall (timeline) | Try to shoutout on your OWN user wall | Blocked with guidance ('post to your feed instead')
B63 | 11. Wall (timeline) | Delete a shoutout you posted | Removed
B64 | 11. Wall (timeline) | (Wall owner) delete a shoutout left on your wall | Removed
12. Messaging (real-time)
B65 | 12. Messaging (real-time) | Start a new conversation with a seller | Conversation opens
B66 | 12. Messaging (real-time) | Send a message | Appears instantly in your thread
B67 | 12. Messaging (real-time) | Send an EMPTY message | Blocked (can't send blank)
B68 | 12. Messaging (real-time) | With recipient logged in elsewhere, send a message | Appears for them WITHOUT refresh (real-time)
B69 | 12. Messaging (real-time) | Open Inbox | Sorted by latest; last-message preview; unread indicator
B70 | 12. Messaging (real-time) | Open a conversation link you're NOT part of | Access denied (can't read others' chats)
13. Notifications
B71 | 13. Notifications | Trigger one (like / follow / order / square request) | Notification appears (bell badge / toast)
B72 | 13. Notifications | Open the notifications panel | List with types and timestamps
B73 | 13. Notifications | Tap a notification | Deep-links to the relevant item
B74 | 13. Notifications | Mark one read; mark all read | Unread count updates correctly
B75 | 13. Notifications | Check a square-request / wall-shoutout notification | Correct type (right icon/label) + working link
16. Final sweep (your areas)
B76 | 16. Final sweep (your areas) | Re-run Seller + Squares flows on a PHONE | Layouts adapt; buttons reachable
B77 | 16. Final sweep (your areas) | Re-check seller screens in DARK mode | Readable, on-brand
B78 | 16. Final sweep (your areas) | Tab through a form with the keyboard (desktop) | Logical focus order; visible focus ring

## Defect Log
Bug ID | Tester | Date | Area / Ref | Device/OS | Theme | Severity | Steps | Expected | Actual | Screenshot link | Status